## Sheet1
ID | Category | Status | Date Raised | Last Update | Raised By | Owner | Author | Cause | Event | Effect | Probability | Impact (monetary) | Proximity | EV | Importance | Response | Description
1 | Technical | Active | 2023-06-14 | 2023-06-14 | Risk Manager | A.S De Silva | A.S De Silva (Risk Manager) | Handling the system for the client might be a challenging task | If the team is unable to find a solution | The client won't be able to perform tasks | 75% to 100% | Rs. 10,000.00 | Next 3 months | Rs. 8,000.00 | High | Risk Acceptance | As this risk is high, provide user manuals for the client
2 | General | Closed | 2023-06-23 | 2023-06-23 | Risk Manager | A.S De Silva | A.S De Silva (Risk Manager) | High product costs could become a challenge | If the team doesn't focus on the issue | The estimated budget might change in the future | 25% to 50% | Rs. 30,000.00 | Next 3 months | Rs. 15,000.00 | High | Rsik Reduction | As this risk is high, make necessary payments without any delays
3 | Technical | Closed | 2023-06-30 | 2023-06-30 | Quality Manager | A.S De Silva | A.S De Silva (Risk Manager) | All the features may not be supported by the planned technologies | If the team is unable to find a solution | Some problems are only discovered during the system's development process | 25% to 50% | Rs. 40,000.00 | This month | Rs. 16,000.00 | Low | Risk Reduction | As the risk is low, can change the technology stack
4 | Technical | Active | 2023-06-30 | 2023-06-30 | Project Manager | A.S De Silva | A.S De Silva (Risk Manager) | Demand for the website may be far higher than expected | If the team developers doesn't solve the issue | The website will become unresponsive or slow | 50% to 75% | Rs. 8,000.00 | Next 3 months | Rs. 5,600.00 | Low | Rsik Reduction | As the risk is low, keep an eye on the website traffic
5 | Technical | Closed | 2023-07-06 | 2023-07-06 | Quality Manager | A.S De Silva | A.S De Silva (Risk Manager) | System overload | If the team developers doesn't solve the issue | It will affect the website's improvement | 50% to 75% | Rs. 20,000.00 | Next 3 months | Rs. 14,000.00 | High | Risk Reduction | As the risk is high, remove unused plugins from WordPress
6 | Technical | Active | 2023-07-06 | 2023-07-06 | Start-up Manager | A.S De Silva | A.S De Silva (Risk Manager) | Completing all tasks within the time period might be a challenge | If the team doesn't divide the tasks between all the members | The website will not be completed within the given time period | 50% to 75% | Rs. 4,000.00 | Next 3 months | Rs. 2,800.00 | Medium | Risk Acceptance | As the risk is medium, manage all tasks within the team properly
7 | Technical | Closed | 2023-07-10 | 2023-07-10 | Quality Manager | A.S De Silva | A.S De Silva (Risk Manager) | Woocommerce is not compatible with every theme | If the team developers doesn't solve the issue | The website will not be completed within the given time period | 25% to 50% | Rs. 12,000.00 | This month | Rs. 4,800.00 | Low | Risk Reduction | As the risk is low, change the theme
8 | Schedule and commercial | Active | 2023-07-13 | 2023-07-13 | Scheduling Manager | A.S De Silva | A.S De Silva (Risk Manager) | Scheduling a meeting with the client was difficult | If the team doesn't communicate propoerly with the client | It will take more time for demonstration and getting approval | 50% to 75% | Rs. 3,000.00 | Next 3 months | Rs. 2,100.00 | High | Risk Reduction | As the risk is high, have propser conversations with the client
9 | Delay of the client | Closed | 2023-07-08 | 2023-07-18 | Risk Manager | A.S De Silva | A.S De Silva (Risk Manager) | The client was late in providing the list of cakes | If the team doesn't focus on the issue | The project team won't be able to manage the planned timeline | 25% to 50% | Rs. 4,000.00 | This month | Rs. 2,000.00 | Medium | Risk Acceptance | As the risk is medium, the team should make necessary arrangements
10 | Schedule | Active | 2023-07-20 | 2023-07-20 | Scheduling Manager | A.S De Silva | A.S De Silva (Risk Manager) | Sudden issues of project team memebers | If the team members doesn't make necessary arrangements | All project-related activities might not happen smoothly | 25% to 50% | Rs. 5,000.00 | This month | Rs. 2,500.00 | Medium | Risk Reduction | As the risk is medium, the team members should have propoer discussions with the project manager
11 | Technical | Closed | 2023-07-27 | 2023-07-27 | Risk Manager | A.S De Silva | A.S De Silva (Risk Manager) | Slow page load time | If the team doesn't focus on the issue | The customers of the website will be affected frequently | 50% to 75% | Rs. 15,000.00 | Next 3 months | Rs. 10,500.00 | Medium | Risk Reduction | As the risk is medium, the team members should remove unnecassary parts and also optimize the images
12 | Technical | Active | 2023-08-02 | 2023-08-02 | Risk Manager | A.S De Silva | A.S De Silva (Risk Manager) | DBMS requires more storage than expected | If the team doesn't focus on the issue | Database performance might be affected by data loss or website downtime | 25% to 50% | Rs. 8,000.00 | This month | Rs. 3,200.00 | Low | Risk Avoidance | As the risk is low, the team members should perform the necessary countermeasures in order to get rid of the issues that might arise