## Report
Caramels and Almonds E-Commerce Website
Earned Value Analysis Report
| Prepared By: | R.S Senarathna
| Date: | 2023-07-21
[42]
| For Period: | Week 5
Summary:
This is the Caramels and Almonds project's earned value analysis report as of week five. The project's complete earned value analysis report shall be made public after completion.
Planned Value (PV)/Cost of work scheduled
WBS | Task Name | TBC | 1 | 2 | 3 | 4 | 5
1 | Domain Purchasing | 5000 | 0 | 0 | 5000 | 0 | 0
2 | Client Requirement | 4000 | 1000 | 1000 | 1000 | 1000 | 0
3 | Purchasing a hosting service | 2000 | 0 | 0 | 2000 | 0 | 0
4 | Website Content | 20000 | 0 | 0 | 5000 | 5000 | 10000
5 | Web Design | 60000 | 0 | 0 | 0 | 20000 | 20000
6 | Integration of an ecommerce platform | 20000 | 0 | 0 | 0 | 20000 | 0
7 | Integration of payment gateway | 10000 | 0 | 0 | 10000 | 0 | 0
8 | SEO | 7000 | 0 | 0 | 0 | 0 | 0
9 | Marketing | 7000 | 0 | 0 | 0 | 0 | 0
10 | Other Expenses | 1000 | 0 | 500 | 0 | 500 | 0
Insert new rows above this one | [7 empty] | ← Insert rows above this one to add other work. Once you have finished adding, you can delete this row..
| Total Budgeted Cost | 136000 | 1000 | 1500 | 23000 | 46500 | 30000
|  | Cumulative Planned Value (PV) | 1000 | 3000 | 30000 | 80000 | 110000
Actual Cost and Earned Value
|  | Cumulative Actual Cost (AC) | 1000 | 2500 | 25500 | 72000 | 102000 | ← Enter the actual costs as calculated from the AC worksheet.
|  | Cumulative Earned Value (EV) | 975 | 2467 | 24100 | 71230.5 | 99230.6 | ← Enter the earned value as calculated from the EV worksheet.
Project Performance Metrics
|  | Cost Variance (CV = EV - AC) | -25 | -33 | -1400 | -769.5 | -2769.4
|  | Schedule Variance (SV = EV - PV) | -25 | -533 | -5900 | -8769.5 | -10769.4
|  | Cost Performance Index (CPI = EV/AC) | 0.975 | 0.9868 | 0.9451 | 0.98931 | 0.97285
|  | Schedule Performance Index (SPI = EV/PV) | 0.975 | 0.82233 | 0.80333 | 0.89038 | 0.9021
|  | Estimated Cost at Completion (EAC) | 139487.1795 | 137819.2136 | 143900.4149 | 137469.2021 | 139795.5872
Note on A21: ====== ID#AAAAWfX7wEc (2022-03-05 17:32:46) Work Breakdown Structure (WBS)
Note on C21: ====== ID#AAAAWfX7wEg (2022-03-05 17:32:46) Total Budgeted Cost (TBC)

## EV
Earned Value Worksheet
Use this worksheet to determine the EV (earned value).
Ensure that the task name, WBS, and TBC match those in the Report worksheet's table.
To determine the cumulative earned value, enter the percent of each task that has been completed.
Cumulative Earned Value (EV)
WBS | Task Name | TBC | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5
1 | Domain Purchasing | 5000 |  |  | 100% | 100% | 100%
2 | Client Requirement | 4000 | 60% | 80% | 80% | 90% | 100%
3 | Purchasing a hosting service | 2000 |  | 50% | 50% | 100% | 100%
3 | Website Content | 20000 |  |  | 50% | 50% | 90%
4 | Web Design | 60000 |  |  |  | 30% | 65%
5 | Integration of an ecommerce platform | 20000 |  |  | 70% | 88% | 100%
6 | Integration of payment gateway | 10000 |  |  | 90% | 90% | 90%
7 | SEO | 7000
9 | Marketing | 7000
10 | Other Expenses | 1000 |  | 50% | 50% | 50% | 50%
Insert new rows above this one
|  | Cumulative EV | 2400 | 4700 | 42700 | 65700 | 97500

## AC
Actual Cost Worksheet
Actual Cost (AC) of Work Performed
WBS | Task Name |  | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5
1 | Domain Purchasing |  |  |  | 4000
2 | Client Requirement |  | 1000 | 1000 |  | 750 | 500
3 | Purchasing a hosting service |  |  | 2000 | 0 | 0 | 0
3 | Website Content |  | 0 | 0 | 2000 | 1000 | 2000
4 | Web Design |  | 0 | 0 | 0 | 10000 | 10000
5 | Integration of an ecommerce platform |  | 0 | 0 | 20000 | 0 | 0
6 | Integration of payment gateway |  |  |  | 0 | 0
7 | SEO
9 | Marketing
10 | Other Expenses |  |  |  | 500
Insert new rows above this one
|  | Total Actual Cost | 1000 | 3000 | 26500 | 11750 | 12500
|  | Cumulative Actual Cost (AC) | 1000 | 4000 | 30500 | 42250 | 54750

## ©
Earned Value Management (EVM) Template
By Vertex42.com
https://www.vertex42.com/ExcelTemplates/critical-path-method.html
© 2012-2017 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet.