## Sheet1
E - commerce website for Caramels and Almonds - Group 05
RACI Matrix
Project Team Members
| Role | Project Manager | Risk Manager | Quality Manager | Start-up Manager | Scheduling Manager
| Name | Pruthuvi Wijesinghe | A.S. De Silva | R.S. Senarathna | H.M. Pumudi Herath | Hasini Jayasekara Vithanage
1 | Gather the Requirements and Define Project Scope and the Objectives | I | C | C | R | C
2 | Accept the Project | R | I | I | R, A | I
3 | Arrange the Client Meeting | I | I | I | I | R
4 | Study the Feasibility of the Project | A | R | R | R | I
5 | Plan the Project Features According to the Objectives | A | R | R | R | R
6 | Act as a Coordinator Between the Stakeholders and the Team Members | R | I | I | I | I
7 | Monitor and Control the Project Members to ensure the Project Execution On Time | R | A,C | A,C | A,C | A,C
8 | Ensure the Quality of the Deliverables | I | I | R | I | I
9 | Perform Quality Testing | I | I | R | I | I
10 | Identify the Possible Risks | I | R | I | I | I
11 | Identify the Mitigations to the Risk | I | R | I | I | I
12 | Create Contingency Budget Plans | I | R | I | I | I
13 | Develop the Project Schedules | I | I | I | I | R
14 | Arrange the Project Meeting | I | I | I | I | R, I
15 | Implement the AI-based Chatbot | I | R | R | C | C
16 | Train the Chatbot | I | R | R | C | C
18 | Project Proposal | I | I | R,A | R | I
19 | Project Brief | I | R | A | I | R
20 | Project Plan | I | R | R,A | R | I
21 | Business Case | R | I | A | I | I
22 | Project Initiation Report (PID) | I | R | R,A | I | R
23 | SRS Report | I | R | R,A | R | R
24 | Gantt Chart | I | R | A | R | R
30 | Daily Log | I | R | A | I | I
31 | Quality Log | I | I | R, A | I | I
32 | Risk Log | I | R, A | I | I | I
33 | Meeting Minutes | I | I | I | I | R, A
34 | Work Breakdown Structure (WBS) | I | R | A | I | I
35 | Product Breakdown Structure (PBS) | I | R | A | I | I
36 | Communication Plan | I | I | A | I | R
37 | Quality Plan | I | I | R, A | I | I
38 | Stage Plans | I | R | A | R | I
39 | Highlight Report 1 | I | R | R,A | I | R
40 | Scope Breakdown Structure (SBS) | I | I | A | R | I
41 | Product Flow Diagram (PFD) | I | R | A | I | I
42 | Precedence Diagram Method (PDM) | I | C | A | R | I
43 | Activity On Arrow (AOA) | I | C | A | R | I
44 | Intergration of Project | C | R | R | C | C
45 | Quality Test Plan | I | I | R, A | I | I
46 | Automated Test Results | I | I | R, A | I | I
47 | Automated Test Summary | I | I | R, A | I | I
48 | Highlight Report 2 | I | R | R, A | I | R
49 | Lesson Learnt Log | R | I | A | I | I
50 | Lesson Learnt Report | R | I | A | I | I
51 | Project End Report | I | R | R,A | R | C
52 | Team Code of Conduct | I | I | A | R | I
53 | User Acceptance Testing | I | I | R | I | I
54 | Meeting Final Expectations | R | R | R | R | R
R | Responsible - Does the work to achieve the tasks
A | Accountable - Responsible for the success/failure of the task
C | Consulted - Provides input for the task
I | Informed - Must be informed about the progress and the output of the task